## Product backlog
Story ID | Priority | Story point | Description | Extra info
20 | 111 |  | Secure the Web API - Authentication - ASP.NET Web Api - Security . MediaTypeFormatter (mapping from Post Json/Xml to object in C#) . Token authentication? . SSL . See bookmarks!
2 | 110 |  | Create registration area (wizzard) | Profile links with Facebook Contains: - Name - Sex - Age (an estimate, i.e. arround 25, or 25-35) - Country - Photo (max 3) - Likes (male/female/both) - Levensmotto
5 | 108 |  | wizzard - Step 1 -> Profile (facebook) + photo (username) | Linked to story 2
4 | 100 |  | Tinder like swipe functionality - browse through contacts (profile, photo, cartoon) - like/no-likey profile or; - slider (left = no-go; right = yes!) geen… hot or not - Online indicator - add Chat button to chat when online
11 | 90 |  | Create chat functionality - Allow to bookmark if both parties agree
12 | 80 |  | Random chat / speed date chat: - max 10 or 5 or 3 minuten - each party indicate to display profile - on the end of chat indicate to continue or not
6 | 50 |  | wizzard - Step 2 -> Cartoon configureren | Linked to story 2
3 | 45 |  | Edit/create moodboard area - Max 16 photo's from Facebook or local (Flickr?, Instagram?) - Option to add text - Able to change the font of the text - Moodboard needs to look like chalkboard - Allow drawings (maybe?) | Get photo's from Facebook
1 | 40 |  | Rating system - More rating based on spend time - Check on language used… - Average time per chat conversation | Part of chatting
7 | 35 |  | wizzard - Step 3 -> Mood board | Linked to story 2
8 | 25 |  | Create chat hotel (framework/functionality) - Max number of people in chat room - Remove inactive people
9 | 24 |  | chat room - Create pub quiz | Boundries: Story 8 need to be finished first
10 | 23 |  | chat room - speed date | Boundries: Story 8 need to be finished first
19 | 20 |  | Create Mobile app

## DoD
Definition of Done
The new feature/page is awesome!
All karma (client side) testing are passed
There is a unit test code coverage of about 50%
All unit tests are passed
Works in all browsers? - IE - Sarari - Chrome - Firefox
Response time < 2 seconden

## Sprint 1
Story ID | Priority | Story point | Description | Extra info
16 | 120 |  | Create design in drawing program (Photoshop or Illustrator) | Part of starting up
14 | 114 |  | Create Front-end project - Scaffold a project with Yeoman (knockout -> yo ko | Part of starting up
15 | 115 |  | Replicate design in HTML, CSS, and Javascript | Part of starting up
13 | 113 |  | Create back-end project - ASP.NET Web Api - Set-up infrastructure (Ninject, Moq, EF6, Tests) - Only exposue Json | Part of starting up
18 | 112 |  | Create Data model - What to store - And what to store